## Sheet1
Stories for the Sprint | Total Hours | Day 1 (Hours) | Day 2 (Hours) | Day 3 (Hours) | Day 4 (Hours) | Day 5 (Hours) | Day 6 (Hours) | Day 7 (Hours) | Day 8 (Hours) | Day 9 (Hours) | Day 10 (Hours) | Day 11 (Hours) | Day 12 (Hours) | Day 13 (Hours) | Day 14 (Hours)
Creating Unit Test for Travis
Routing for Pages
Profile Page Format
Form to get Update User Information
Display User's Info in Profile Page
Change Profile Picture | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
User's Wants on Profile Page
User's "I Want This" Page listing their wants
Most Liked Wants on Home Page | 6 | [8 empty] | 3 | 3
CSS change
Fetch data using User ID
Refactor Code
Confirmation before Deleting, Adding, Editing Wants
Footer not on bottom bug
Sub Category Bug
Restriction to Deletion of Wants
Delete a Want must remove it from "I want this" Page
Remaining Effort | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 4 | 1 | 1 | 0 | 0 | 0
Ideal Burndown | 7 | 6.5 | 6 | 5.5 | 5 | 4.5 | 4 | 3.5 | 3 | 2.5 | 2 | 1.5 | 1 | 0.5 | 0
Stories Remaining | 17 | [9 empty] | 16 |  | 15
Stories Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 0