## Table Sprint 4
Stories for the Sprint 4 | Total Hours | Day 1 (Hours) | Day 2 (Hours) | Day 3 (Hours) | Day 4 (Hours) | Day 5 (Hours) | Day 6 (Hours) | Day 7 (Hours) | Day 8 (Hours) | Day 9 (Hours) | Day 10 (Hours) | Day 11 (Hours) | Day 12 (Hours) | Day 13 (Hours) | Day 14 (Hours)
Creating Unit Test for Travis | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Routing for Pages | 6 | 1 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Profile Page Format | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 0
Form to get Update User Information | 11 | 1 | 1 | 3 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 1 | 1 | 0 | 0
Display User's Info in Profile Page | 13 | 1 | 1 | 0 | 0 | 0 | 0 | 4 | 1 |  | 0 | 2 | 3 | 1 | 0
Change Profile Picture | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
User's "I Want This" Page listing their wants | 6 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Most Liked Wants on Home Page | 6 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 1 | 0 | 0
CSS change | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 6 | 8 | 0 | 0
Communicate Between Collections | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
Refactor Code | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
Bug fixing | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
Putting want cards in want page | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0
Remaining Effort | 76 | 71 | 65 | 57 | 57 | 57 | 53 | 41 | 40 | 40 | 30 | 19 | 2 | 0 | 0
Ideal Burndown | 76 | 70.5714 | 65.1429 | 59.7143 | 54.2857 | 48.8571 | 43.4286 | 38 | 32.5714 | 27.1429 | 21.7143 | 16.2857 | 10.8571 | 5.4286 | -2.3093e-14
Stories Remaining | 13 | 13 | 13 | 11 | 11 | 11 | 11 | 10 | 10 | 10 | 7 | 6 | 2 | 0 | 0
Stories Completed | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 6 | 7 | 11 | 13 | 13

## Table Sprint 5
Stories for the Sprint 4 | Total Hours | Day 1 (Hours) | Day 2 (Hours) | Day 3 (Hours) | Day 4 (Hours) | Day 5 (Hours) | Day 6 (Hours) | Day 7 (Hours) | Day 8 (Hours) | Day 9 (Hours) | Day 10 (Hours) | Day 11 (Hours) | Day 12 (Hours) | Day 13 (Hours) | Day 14 (Hours)
CSS for Profile Page (Mario) #138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CSS for WebPage #95 (Seb, Siamak) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CSS for WebPage #147 (Josh) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Title of Ad to Ad Page #130 (Arnav, Siamak, Josh) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Populate Ad Page #131 (Arnav, Josh, Siamak) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Add Pictures to Ad #132 (Arnav, Josh, Siamak) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Makers/Wanters Visible on Add #134 (Arnav, Josh, Siamak) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Website Small Modifications #150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Model Software with Architecture(Arnav) #136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Travis Test Cases #57 (Nick) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Momo's Bug Fixes (includes Footer at Bottom, deletion of a want, parsing date/time) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remaining Effort | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal Burndown | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Stories Remaining | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Stories Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0